## CR
Scheme Description |  |  |  | Status | Cost | Timescales (short, medium & long term) | Economy |  | Effectiveness |  | Policy |  | Deliverability |  | Connectivity |  | Prioritisation
Ref. | Route | Section | Description |  | Estimate Cost (where feasibility work has been undertaken) | Choose between short, medium & long term) | Value score - based on distance and number of additional cyclists | Partial funding available | Forecast increase in the number of cycling trips | Improvement in road safety | Improved transport connections | Provides a route to school | Scheme feasibility or deliverability | Environmental constraints | Integration with other schemes | Contribution of the scheme to the overall network development | Total score
1 | Ely North - Ely Centre - Ely Station | Ely Centre - Ely North | Developers may provide some of cycle route along Lynn Rd but for southern section of Lynn Rd by developers in question due to feasibility issues, particularly parking. Consider changes to road allocation to provide space for segregated cycleways informed by the Sustrans feasibility design work. | some feasibility work undertaken |  | medium/long | 2 | 1 | 3 | 2 | 3 | 1 | 1 | 2 | 3 | 2 | 20
|  | Ely Centre - Ely Station | As above, road re-allocation needs to be considered to provide segregated cycleways on Back Hill and Station Rd. Options considered as part of Active Travel Tranche 2 project but further work needed on wider implications. Some improvements undertaken as part of Broad St junction safety scheme and removal of car parking as part of the Active Travel scheme. Access to the station itself needs to be improved with a safe crossing. Longer term a route to the station as part of new developments to be considered through the Marina and industrial area to Station Rd which would include a new bridge. | some improvements and feasibility work undertaken
2 | Ely Station - Ely South West - Witchford | Ely Station - Ely South West | Back Hill & Station Road: as above. Barton Road: install cycle symbols, traffic calming measures and make the area a 20mph zone. Improve surfacing of traffic calming where necessary. Upgrade zebra crossing to a parallel crossing and widen off-road link to Witchford Road, Witchford Road:widen existing shared-use path to 3 metres wide and consider solar studs. |  |  | short/medium | 1 | 1 | 3 | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 19
|  | Ely South West - Witchford (this may change depending on works to A10) | New cycle/ped crossing of A10, preferably as a bridge or underpass Widen existing shared-use path on A142 to 3m to the Lancaster Way junction and install solar studs. . Improve route into business park and into Witchford. Witchford Rd: widen shared use path where possible to 3m and consider traffic calming measures along Main St and widen existing path as exit village to A142 to link to existing route to Sutton. Longer term provide route to the north through new development as proposed by the Parish Council. | Feasibility work on crossing options underway.
3 | Fordham - Soham |  | Consider road re-allocation through Fordham as set out in the Sustrans feasibility study. Improve existing shared use path on Fordham Rd and add solar studs where unlit. Improve approaches to cycle/ped bridge over the roundabout. Consider on-road provision through Downfields and on Sand St with traffic calming measures. Continue traffic calming through High St and through to new station via Clay St and Station Rd. Provide cycle lanes and/or traffic calming on Townsend. | Some feasibility work undertaken. |  | medium | 1 | 0 | 2 | 2 | 3 | 2 | 2 | 2 | 2 | 1 | 17
4 | Ely Centre - Ely North West/ leisure centre |  | Downham Rd/ West Fen Rd: as above consider changes to traffic management and road re-allocation such as one-way systems in order to provide for cycling as set out in the Sustrans Ely to Little Downham feasibility study . Change layout of the Cam Drive/Downham Rd roundabout to a more compact design to reduce speed and improve cycle crossings or consider a dutch style arrangement. Provide link between proposed new junction on north side of Cam Drive and roundabout on Downham Rd. Improve links to and through the leisure centre as set out in the feasibility report and install additional cycle parking. | some feasibility work undertaken |  | short | 1 | 1 | 2 | 2 | 0 | 3 | 2 | 3 | 2 | 1 | 17
5 | Soham to Wicken |  | Feasibility work undertaken by Sustrans and partial funding provided for further work by CPCA. | Costing and design work being undertaken. |  | short | 0 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 16
6 | Lode - Waterbeach |  | On road along the droveway. Negotiate land to convert footpath to cycleway and build structure across lode and build cycleway to Bottisham Lock then link to Bannold Rd. May be developer funding to upgrade footway to bridleway. |  |  | medium | 0 | 1 | 1 | 1 | 3 | 1 | 1 | 2 | 3 | 3 | 16
Scheme Description |  |  |  | Status | Cost | Timescales (short, medium & long term) | Economy |  | Effectiveness |  | Policy |  | Deliverability |  | Connectivity |  | Prioritisation
Ref. | Route | Section | Description |  | Estimate Cost (where feasibility work has been undertaken) | Choose between short, medium & long term) | Value score - based on distance and number of additional cyclists | Partial funding available | Forecast increase in the number of cycling trips | Improvement in road safety | Improved transport connections | Provides a route to school | Scheme feasibility or deliverability | Environmental constraints | Integration with other schemes | Contribution of the scheme to the overall network development | Total score
7 | Exning - Fordham |  | Need to work with Suffolk County Council to provide route within Suffolk boundary . The Sustrans feasibility study provides options for improving the route including a point closure on Landwade/Cotton End Rd and a crossing of the A142 and a segregated cycleway to Fordham. | Some feasibility work undertaken |  | medium | 0 | 0 | 2 | 3 | 1 | 0 | 1 | 2 | 2 | 3 | 15
8 | Ely Centre - Ely North East |  | Consider traffic calming/reduction in town centre area. Prickwillow Rd: consider traffic calming measures and advisory cycle lanes where feasible. Widen cut through at the end of Sycamore Lane and provide cycle/pedestrian bridge to link from Summerhaze to Merivale Way . |  |  | short | 0 | 1 | 1 | 2 | 1 | 1 | 2 | 3 | 2 | 2 | 15
9 | Stuntney - Ely |  | Consider options to improve route along A142 such as narrowing carriageway, piping ditch and negotiating land. |  |  | medium | 0 | 1 | 1 | 2 | 1 | 2 | 1 | 2 | 2 | 3 | 15
10 | Witcham to Witchford/Sutton and links to Elean Business Park | Mepal to Sutton | Provide safe crossing of A142 at junction with byway to Mepal and widen path into Sutton or provide off-road path along A142 |  |  | short | 0 | 0 | 1 | 3 | 0 | 3 | 2 | 3 | 1 | 2 | 15
|  | Sutton to Elean Business Park | Widen path to roundabout and provide safe crossing of roundabout to business park.
|  | Witcham to Sutton | Consider modal filter on The Slade or widen path where possible. Widen path to crossing of A142 towards Witchford. Reduce speed limit to 40mph through Witcham Toll and consider formal crossing to facilitate route to school. Provide safe crossing at junction and build short section of shared use path to refuge crossing A142 to link to existing route to Sutton. Spade out existing path and install solar studs. Continue segregated route into Sutton centre.
11 | Ely - Littleport |  | Widen existing path adjacent to the carrriageway and extend to Littleport. This may require piping of the ditch and/or land negotiation. Developer funding for improvements to path up to Chettisham. Alternatively investigate possibility of providing a shared path along Branch Bank though likely to be difficult given the levels. Options will be informed by Sustrans feasibility study currently underway. | Feasibility study underway |  | short/medium | 1 | 1 | 2 | 3 | 0 | 0 | 1 | 2 | 1 | 3 | 14
12 | Ely Centre - Ely West |  | West Fen Rd: Consider traffic calming measures and on-road advisory cycle lanes with removal of centre line or road reallocation options. |  |  | short | 1 | 0 | 1 | 1 | 1 | 0 | 2 | 3 | 2 | 2 | 13
13 | Little Downham - Ely |  | Route along Hurst Lane or along the B1411 with options set out in the Sustrans feasibility study . | Feasibility study undertaken |  | medium | 0 | 1 | 2 | 1 | 1 | 1 | 2 | 2 | 1 | 1 | 12
14 | Burwell - Swaffham Prior |  | Consider options set out in Sustrans feasibility study. | Feasibility study undertaken |  | medium | 0 | 0 | 0 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 12
15 | Reach - Burwell |  | Provide shared path next to Burwell Rd |  |  | medium | 0 | 0 | 0 | 3 | 0 | 0 | 2 | 1 | 2 | 2 | 10
16 | Isleham - Fordham |  | Provide shared path next to Isleham Rd |  |  | medium | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 9